## Sheet1
Area | Dept | NO | Project | Deliverable | Project Start date | Project End Date | Next step(s) | Next Step Due date | Owner | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Notes
Administration & IT | IT | 1 | Document Management/Collaboration | No Information - Is this a project? | 2014 | 2016-01-01 | Project Charter & Project Plan | 2015-06-21
Milestones –Moved to Communications
|  | 2 | Incident Tracking | No Information - Is this a project? | 2014-01-01 | 2015-06-15 | Roll out the tool | 2015-06-15
| Administration | 3 | Process for venue selection | No Information - Is this a project? |  |  | Building the team | N/A
| Knowledge Mgt |  | Training for Google Sites-not a project | No Information - Is this a project?
|  | 4 | Design Repository Structure for all chapter documents | No Information - Is this a project? | 2015-03-01 | 2015-10-01 | Project Charter | 2015-06-21
| Business Analysis and Process Mgt |  | Business Process management Program-not a project | No Information - Is this a project?
|  |  | Chapter Process & Procedure Standards- not a project | No Information - Is this a project?
Communications | Outreach | 5 | Establish Academic, Corporate and Non Profit Outreach | Formal Relationships with selected organizations | 2015-05-01 | 2016-03-31 | Resource Recruitment | 2015-08-27 | Mary Sidhom | Notes: Director Outreach stepped down 5/10/15; Plan start in August
| Sponsorship and Advertising | 6 | Update Advertising/Sponsor packages for bundled options | Updated Advertising & Sponsorship Packages/Kits | 2015-05-01 | 2015-12-30 | Ongoing | 2015-12-30 | Mary Sidhom | bar: May
| Sponsorship and Advertising | 7 | Develop Contract Agreement process | A formal contract process for Sponsors/Advertisers | 2015-05-01 | 2015-12-30 | Ongoing | 2015-12-30 | Mary Sidhom | bar: May
| Postcard and Calendar | 8 | Template for postcard | Template for Postcards for printing | 2015-04-01 | 2015-05-01 | Complete | Complete | Shahrzad Tajmiri | Notes: Complete
| Milestones | 9 | Milestones project | Contract with outside vendor for Milestones | 2015-04-15 | 2016-01-30 | Merge with Outsource | 2016-01-30 | Jaime Dias | Notes: PM Stepped down 5/20/15; Being rolled up with Marketing Outsourcing Project
| Marketing | 10 | Outsource Web and Print Craetive Activities | Contract with outside vendor for marketing services | 2015-04-15 | 2016-01-30 | Proposal Finalization | 2016-01-30 | Jaime Dias | Notes: Vendor shortlisted; Proposal for BOG on 5/28/15
Finance | Registration | 11 | Mobile app and upload PDUs at the door (Potential) |  |  |  | Vish to explore for 2 weeks
Operations | Special events | 12 | Annual event | Successful 2016 Annual Event; lessons learnt; break even/profit. | ??? | 09/31/2016 | Recruit Director and form team | 2015-07-24 | Rod Hendrixon*
| Dale Carnegie |  | Dale Carnegie event- cancelled | Cancelled
| Career Workshop | 13 | Career Workshop | Need Additional Information |  |  | Project Charter | 2015-07-14 | Gary Reknar
| PMP Worskshop | 14 | PMP/CAPM Certification Exam Updates | Need Additional Information |  |  | WBS | 2015-07-14 | Gary Reknar
| All areas |  | CCR Updates | Need Additional Information |  | TBD | Project plan | TBD | Gary Reknar
Strategic Planning | Strategic Planning |  | Chapter Maturity Assessment- not a project just a big operational activity |  |  |  | Project Plan
Strategic Planning
| Membership | 15 | Membership Outreach | Need Additional Information | 2015-07-01 | 2015-12-31 | Project charter, project plan | 2015-07-31
|  | 16 | Student Discount Program | Need Additional Information | 2015-08-01 | 2015-12-31 | Need more information, Project charter | 2015-08-30
| Volunteers | 17 | Research, develop and document efficient processes for volunteer management | No Information - Is this a project? |  |  | Project charter
Update the VOM information on the website-not a project
* Temporary until position is filled